2015-2018

John Noble Home

Operational Plan Template

|  | OPERATIONAL OBJECTIVES | ACTIONS | DELIVERABLES | RESOURCES | MEASURES OF SUCCESS | TIMELINE | STATUS REPORT |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BALANCED SCORE CARD -INTERNAL PROCESSES-SAFE AND QUALITY OPERATIONS |  |  |  |  |  |  |  |
| 1 | Compliance with all regulatory bodies (MOHLTC, MOL, Fire, Public Heath) | - MOHLTC - MOL - Fire - Public Health - LHIN and HQO and others bodies with reporting requirements | - Regular inspections using RQI audits and protocols. Follow up with any unmets - Regular inspections and Health and Safety Meetings - Annual fire inspections and 3 fire drills/month. Also update fire plan - Dietary and food handling inspections and infection control audits. - Staff education for all new staff and annual staff education. Targeted education for any areas of under performance - Compliance with LHIN and HQO and other reporting bodies - Mock inspections | - MOHLTC revised RQI audits. - iPharm - MOL | - Minimal findings | Ongoing | Quarterly |
| 2 | Continue Accreditation preparations | - Review Primer results and address any areas of concern. - Continue preparations for full Qmentum survey in two years | - Update any policies or procedures required for accreditation - Follow up on action plans associated with Accreditation - Develop various plans or safety or risk management analysis as required by Accreditation Canada - Staff education on Qmentum process - Mock survey | - Accreditation Team - Quality Improvement/Risk Coordinator - Administrator - Senior Management - Staff Educator | - Successful Accreditation | 2 Years | Quarterly |
| 3 | Continue Departmental Quality, Risk Management and Safety Initiatives | - Each department is responsible for annual quality, risk management and safety initiatives as well as those that are operational to be classified by our balanced scorecard themes | - Identify a quality initiative, prepare a charter statement, and define measures, track and attached timelines for measuring successes for each imitative. | - Health Quality Ontario - Quality Improvement/ Risk Coordinator - CIHI - Point Click Care | - Benchmark of 90 % or greater - Action Plan for those less than 90% | Ongoing | Monthly/Quarterly |
| 4 | Increase attention to dementia care and responsive behaviours | - Look at best practices review lighting and environmental design | - Provide ongoing educate to all staff to increase knowledge base - Support ongoing learning in and outside the home for capacity building - Network with other Long Term Care Facilities for successful design opportunities related to dementia care | - Staff educator - Alzheimer’s Society - SHRTN - RNAO Best Practice Co-coordinator - RNAO Best Practice Guidelines - John Noble Home Day and Stay Program | - Reduced number of BSO referrals from admission/ transitional program and stand alone referrals. - Reduced injuries related to resident to resident responsive behaviors(CIS reporting). | Ongoing | Monthly/Quarterly |
| 5 | Pursue capital projects that enhance and promote safety and security | - Identify projects for 10 year capital plan - Priorities are asbestos, mould, fire suppression, swipe cards, outdoor and indoor lighting, paving) | - Get quotes and define project scope in 2015 - Prioritize safety risk and submit for annual capital - Update 10 year capital plan as required as needs change or arise | - Environmental Services Manager - City/County - JNH COM - Administrator | - Compliance with the MOHLTC/MOL standards for the physical environment - Maintain costs within resources available | 10 year | Yearly |
| 6 | Review and update existing governance policies overseeing John Noble Home and its Board with the Committee of Management | - Reduce and streamline any governance policy on procedure which needs to be updated. Especially those which cause delay in operations. | - New governance policies | - Administrator - City/County - JNH COM | - Updated governance policies. | Yearly | Monthly |
| BALANCED SCORE CARD -FINANCIAL ACCOUNTABILITY/RESPONSIBLE USE OF RESOURCES |  |  |  |  |  |  |  |
| 1 | To introduce systems to support financial sustainability | - To employ the use of outside resources and more up to date technology to streamline internal process. | - City/County - Consultation to update systems. | - City/County - Administrator - COM | - Streamlined update systems | Monthly | 3 years |
| 2 | Continue to explore collaboration opportunities with City, County or others regarding efficiencies associated with Payroll, HR, IT and other back office functions. | - To employ the use of outside resources and more up to date technology to streamline internal process. | - City/County - Consultation to update systems. | - City/County - Administrator - COM | - Streamlined update systems | Monthly | 3 years |
| 3 | Reduce the facility-related financial demands on the annual operating budget | - To investigate cost saving efficiencies with the current infrastructure - Ensure current operating equipment is maintained in good order to extend life expectancy. | - Cost Saving Efficiencies implemented - Preventative Maintenance Program enhanced | - Environmental Services Manager - Maintenance Department - Administrator - Department Manager | - Remain within budgeted costs for the physical operations of the home - Remain in budget for equipment maintenance and repair | Monthly | Monthly |
| 4 | Increase preferred revenue and pursue revenue generating opportunities or other public private partnerships. | - To work with CCAC, financial and nursing to ensure admissions are placed in appropriate accommodation type. - Network with community programs for optimal utilization of decommissioned space | - Audit of residents in appropriate level of accommodation related to payment type - Attend and participate in community discussions and committees | - City/County - JNH COM - Administrator | - Preferred accommodation revenue increased. - Revenue generated through partnerships/added services | 3 years | Monthly |
| 5 | Review fundraising policies and opportunities for donations or grant programs for different Program areas | - Meetings with City/County to clarify and establish fund raising abilities in the home. - To develop policy and process that will make the public aware of our fundraising abilities and encourage participation. | - Clear policy and procedure on fund raising in the home. | - JNH COM - Administrator - Department Managers | - Donations and grants received increased. | Ongoing | Monthly |
| 6 | Implement 10 year capital projects plan and update as required | - Current facility assets in the home reviewed through the 10 year plan. - Investigation of life expectancy of equipment in the home and the replacement timelines required. | - Current and accurate 10 year capital projects plan. | - JNH COM - Administrator - Department Managers | - 10 year plan on target - 10 year plan updated as required | Ongoing | Monthly |
| 7 | Continue the Senior’s Hub initiative and explore how to share services and reduce overhead costs | - Engage professionals to conduct a report on the possible expansion of the current space available. - Network with community services to determine the community needs in partnership with the Master Aging Plan. | - Partnerships developed with the community stakeholders. - Business Plan Developed for the vacant areas. | - JNH COM - Administrator | - Seniors Hub activity in progress | 3 years | Quarterly |
| BALANCED SCORE CARD -CONTINUOUS EDUCATION, GROWTH, INNOVATION AND TECHNOLOGY |  |  |  |  |  |  |  |
| 1 | To enhance education program | - Investigate software to support the delivery of education in the home. | - Implementation of new software to support the education of staff. | - HR Generalist - Staff Educator - Department Managers | - Enhancements made to education program | 1 year | Monthly |
| 2 | To educate staff regarding Accreditation | - Creation of the Qmentum Teams. - Utilization of Accreditation Canada resources for the Qmentum Process. | - Qmentum Teams implemented - Qmentum education developed with an internal education plan. - Roadmap to full Qmentum implemented | - Accreditation Coordinator - Qmentum Team - Administrator - Department managers | - Ongoing communications provided - Staff preparedness quiz demonstrates knowledge transfer - Meeting roadmap targets as set out by Accreditation Canada. | Ongoing 2015-16 | Monthly |
| 3 | To redevelop web design | - Web design team continues with city representative to finalize content. | - New Web site live and connected to the city IT network. | - City - Financial Services Manager. - QI/RM Coordinator - Website review team | - Website connected with City - Plan for ongoing updating in place | 2015 | Monthly |
| 4 | To enhance information technology capabilities | - To engage in the Smart Community Initiative. | - Increased wireless technology for staff, public, and caregivers. | - City/County - Financial Services Manager | - IT deliverables in place | Ongoing | Monthly |
| 5 | Enhance use of information technology in all Program areas including the introduction of eMAR implementation (Electronic Medication Administration) for long term care | - Collaboration with contracted pharmacy to implement eMAR - Implementation of educational plan for staff preparation for eMAR use. - Investigation of policy and procedure to support eMAR and emergency contingencies. | - Functional eMAR - Policy and procedure to support eMAR use - Staff preparation education completed. | - Department Managers - DOC/ADOC - iPharm | - eMAR implemented | 2015 | Monthly |
| 6 | Create an information and technology plan | - Explore possible future partnerships and IT needs of the home. | - IT plan created | - Administrator - Financial Services Manager - Department Managers | - IT plan in place | 2015 | Monthly |
| 7 | Further explore the introduction of WIFI, SKYPE and its use in all areas of the Home and its different programs | - To engage in the Smart Community Initiative. | - Increased wireless technology for staff, public, and caregivers. | - City/County - Financial Services Manager - Administrator | - IT deliverables in place | Ongoing | Monthly |
| 8 | Increase education of general public and consumers of care about aging process, dementia, application to John Noble Home’s different Programs | - To maintain an updated and current website. - Continue to support outside resources in education plans with offering space for forums. - To create community partnerships that give educational opportunities. - Update current printed material for circulation to various community partners. | - Current website - Community Partners participating in the utilization of vacant space. - Printed material will be refreshed and better reflect the homes programs and services. | - Administrator - Department Managers - Admission Coordinator | - Maintained or increased appropriate referrals to LTC, Housing and the Day and Stay Program. | Ongoing | Quarterly |
| 9 | Participate in external committees and initiatives | - Department Managers will engage with outside initiatives and working groups. | - Information sharing with external resources | - Administrator - Department Managers | - Active membership on external committees and initiatives. | Ongoing | Monthly |
| 10 | Increase collaboration with local schools and universities as well as community partners | - Participate in opportunities available with various educational institutes | - Partnerships developed and contracts engaged | - Administrator - Department Managers - Staff educator | - Increase in student opportunities | Ongoing | Quarterly |
| 11 | Enhance research efforts or involvement in new best practices (i.e. BPSO- best practice spotlight organization). | - Continue being host of RNAO LTC Best Practice Coordinator - Participate in DOC BP meeting with coordinator - Explore resources and readiness for BPSO participation possibilities if offered. | - Readiness plan in place to further consider participation in BPSO program | - Administrator - DOC/ADOC - RNAO Best Practice Coordinator | - Research opportunities explored - BPSO application submitted if RNAO makes further offer for expression of interest application. | 3 years | Quarterly |
| 12 | Pursue opportunities for expansion within all Program areas at John Noble Home to use vacant or idle space or land. | - Engage professionals to conduct a report on the possible expansion of the current space available. - Network with community services to determine the community needs in partnership with the Master Aging Plan. | - Partnerships developed with the community stakeholders. - Business Plan Developed for the vacant areas. | - JNH COM - Administrator | - Seniors Hub activity in progress | 3 years | Quarterly |
| BALANCED SCORE CARD -CUSTOMER SATISFACTION |  |  |  |  |  |  |  |
| 1 | Annual resident, family, Adult Day Program client and tenant and staff satisfaction surveys | - Plan process for annual resident/client survey - Plan process for staff survey in correlation with Accreditation Canada work life pulse assessment requirements - Plan process for annual tenant survey | - Resident/Client survey completed - Staff satisfaction survey completed - Tenant survey completed | - Administrator - Coordinator of Resident Programs - QI/RM Coordinator - Day and Stay Manager | - Increase of satisfaction overall by resident, clients, staff and tenants | Annually 2015-2018 | Quarterly |
| 2 | Communication and Marketing plan | - Develop a communication and marketing plan - Update web site | - Communication and Marketing plan created - Website updated and connected with City site - Renew and update all marketing materials | - Administrator - Admissions Coordinator | - Plan implemented and on target - Maintained or increased appropriate referrals to LTC, Housing and the Day and Stay Program. | 2015 | Monthly |
| 3 | Create a Communication and Marketing Plan (renew marketing material and web site) | - Develop a communication and marketing plan - Update web site | - Communication and Marketing plan created - Website updated and connected with City site - Renew and update all marketing materials | - Administrator - Admissions Coordinator | - Plan implemented and on target - Maintained or increased appropriate referrals to LTC, Housing and the Day and Stay Program. | 2015 | Monthly |
| 4 | Annual surveys within each Program (LTC, Day and Stay, Tenants) with action plans for indicators below 90% | - Plan process for annual resident/client survey - Plan process for staff survey in correlation with Accreditation Canada work life pulse assessment requirements - Plan process for tenant survey | - Resident survey completed - Staff satisfaction survey completed - Tenant survey completed | - Administrator - Coordinator of Resident Programs - QI/RM Coordinator - Day and Stay Manager | - Increase of satisfaction overall by residents, clients, staff and tenants | Annually | Quarterly |
| 5 | Create a human resources plan | - Utilize Accreditation Canada’s resources to develop HR plan | - HR plan developed | - Administrator - Human Resources Generalist - Department Managers | - Succession plan in place - Mentorship program enhanced | 2015 | Monthly |
| 6 | Enhance signage internally and externally to better identify the different programs and their location. Add an electronic sign out front | - Needs assessment for signage required. - Investigate electronic signage sources and associated costs. | - Needs identified with plan to implement signage needs. - RFP process through city for electronic signage | - Environmental Services Manager - Administrator | - Increase signage externally - Electronic sign out front | 2015-2016 | Monthly |
| 7 | New staff room and review of staff health and wellness initiatives | - Obtain quotes for new staff room - Review of Health and Safety Committees goals to enhance the program | - New staff room created - Staff have increased health and wellness programs | - Administrator - HR Generalist - Health and Wellness Committee | - Increase staff satisfaction related to health and wellness programs. - Staff space available | 2018 | Quarterly |
| 8 | Explore with tenants and clients in the Day Program what other outreach or support services can be added to help them remain independent and in their homes. | - To review the results of the annual surveys and community needs assessment to determine identified high needs areas - Investigate the financial and environmental space feasibility. | - An action plan for implementation of the identified high needs. - Cost and physical space analysis complete. | - Day and Stay Manager - Administrator - Brant Housing | - Added services for the Day and Stay program and housing that meet the needs identified by the clients. | 2015 | Monthly |
| 9 | Continue to offer door to door transportation for clients of the Day Program and purchase/lease another bus or vehicle to keep up with service demand | - Commence fundraising for transportation - Investigate grant opportunities from Community organizations | - Funds available to purchase or lease a new bus. | - Administrator - Day and Stay Manager | - Door to door transportation continues - New bus in operation | 3 years | Monthly |
| 10 | Continue to maintain or enhance the physical environment (internal and external) which promote therapeutic, healing and leisure activities | - Conduct site review to identify opportunities to enhance the internal and external environment - To investigate future therapeutic and leisure enhancement programs | - Identified areas for possible expansion of current programs - Identified programs that will increase the therapeutic and leisure and healing activities of the home. | - Administrator - Environmental Services Manager - Coordinator of Resident Program/Volunteers | - Increased therapeutic recreation, healing and leisure programs | 3 years | Quarterly |
| 11 | Work with City and County Council and our Committee of Management to meet emerging needs of aging constituents and/or their caregivers. | - Investigate revenue generating partnerships to fund future projects. | - Increased revenue to facilitate provision of added programs to meet the needs of the elderly and their care givers in the community. | - City and County - COM - Administrator | - Increased revenue | 3 years | Quarterly |